## Slide 1: TERRE Trans European Replacement Reserves Exchange
EBSG meeting
01st July 2019

## Slide 2: Topic 1: Introduction from TSOs and NRAs

## Slide 3: 1. Introduction
The following countries plan to use Replacement Reserves:
Region 1
  France (RTE) - CRE
  Italy (TERNA) - ARERA
  Portugal (REN) - ERSE
  Spain (REE) - CNMC
  Switzerland (SG) - Elcom
  Great Britain (NG) - Ofgem
Region 2
  Poland (PSE) - URE
  CZ (CEPS) - ERU
Region 3
  Romania (TEL) - ANRE
  Hungary (MAVIR) - MEKH
  Bulgaria (ESO) - DKER
Observers:
  Greece (ADMIE)
  Nordic area
RR TSO
Non RR TSO
TERRE project - Participating TSOs & NRAs

## Slide 4: 1. Introduction
High level planning
Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
TERRE Platform Implementation
2018
Legal
Approval
Design
Implementation
GO Live window
2019
Today
Start-up stage
//run
RRIF draft
Define future LIBRA operational framework
RFP phase lot C
Launch B1/B2/F services
Launch Lot C services
RRIF PC and assessment
RRIF validation by NRAs
B1/B2 Design stage
B1/B2 Development stage
B1/B2 FAT stage
RFP phase lot D
RFP phase lot E
Launch Lot D services
Launch Lot E services
RRIF Validated
UAT
IOP
B1: Optimization Module; B2: Data Management Module; F: Testing; C: Hosting; D: IT monitoring; E: Financial service

## Slide 5: Topic 2: RR pricing and TSO-TSO settlement rules applied for the RR Platform Go-Live

## Slide 6: 2. RR pricing and TSO-TSO settlement rules applied for the RR Platform Go-Live
Highlights
Pricing proposal (link)
Article 3: General principles
Article 4: Additional Provisions for the Pricing of Standard RR Balancing Energy Product Bids
TSO-TSO settlement proposal (link)
Article 6: Settlement of the intended balancing energy activated for system constraints purposes
When TERRE goes live, to simplify the calculation, the extra cost due to constraint will be equally paid by the TSOs who evoke the request. In a later stage it will be divided proportionally to the sum of the differences between the flow from CC run and UC run on each interconnector
These rules will be implemented for TERRE go live but may change in the future because the proposals are still not validated by ACER

## Slide 7: Topic 3: Algorithm Optimisation Function description-part 1

## Slide 8: 3. Algorithm Optimisation Function description-part 2
The existing implemented solution in LIBRA allows counter-activations but as agreed in the RRIF, TERRE will monitor counter-activations during the first year of operation and the project is working on solutions to limit them
Potential prevention of counter-activations:
  Theoretical formulation
  Implementation has not yet been done
  Not possible to conclude if this option can return a feasible solution within the specified time limit
Existing solution
Proposal for minimizing counter-activations
Optimization Algorithm – Counter-activations’ treatment

## Slide 9: 3. Algorithm Optimisation Function description-part 2
Splitting of needs and bids
Needs
Bids
Need-to-need
Need-to-bid
Bid-to-need
Bid-to-bid
Objective function
Maximize: Need satisfaction + Need matching surplus – Counter activations
Optimization Algorithm – Counter-activations’ treatment

## Slide 10: 3. Algorithm Optimisation Function description-part 2
Example (1/2)
Inputs:
ATC does not affect the results
Optimization Algorithm – Counter-activations’ treatment

## Slide 11: 3. Algorithm Optimisation Function description-part 2
Example (2/2)
Outputs:
Optimization Algorithm – Counter-activations’ treatment

## Slide 12: Topic 4: RR process timing

## Slide 13: 4. RR process timing
Timeline
H-70min
H+60 min
H
H-35min
H-40min
H-60min
RR Balancing Energy Gate Closure Time
TSO Energy Bid Submission Gate Closure Time
Delivery period
Activation period
Results communication and verification phase
Clearing phase
Tendering phase
Pre-tendering phase
TSO responsibility
Common platform responsibility
TSO responsibility
- BSPs submit offers
to TSOs
- submit imbalance needs
- submit offers
- submit ATC
- submit HVDC constraints and schedules (optional)
- allocate offers to needs
- determine prices
- calculate XB schedules
- Activate offers
- send accepted offers
& satisfied needs
- send XB schedules
- send clearing prices
- send remaining ATC
- send net positions
Common
platform
responsibility
- Submit transparency data
Adjusted to H-55 end of 2020*
RR process consists of the following phases:
  pre-tendering phase
  tendering phase
  clearing phase
  results communication and verification phase
  activation phase
  delivery phase
H-30 min
TSO BSP communication period
  * Ongoing assessment to determine whether all TSOs will be able to meet this deadline knowing the go live dates are postponed

## Slide 14: Topic 5: Parallel Run phase, BSP involvement and planning for Go-Live(s)

## Slide 15: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
Verify correct interaction of platform and TSO systems when all connected – prove that configuration is correct and all data & message paths fully functional
Check on operational procedures and exception handling, including human communication paths and processes, fall-back procedures
Demonstrate end-to-end process operation
Gain experience of result of optimisation with data as close to “real-life” as possible
Confirm readiness for Go-Live
Objectives

## Slide 16: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
All platform functions including financial outputs
West Region only – all TSOs in the region (though not necessarily starting at the same time)
All bid types
Use of Desired Flow Ranges
Area de-coupling
Scope

## Slide 17: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
These new forecasts will require requests for derogation which will be submitted to NRAs for approval
Go live forecasts
TSO | Go live forecast
CEPS | December 2019
REE | Q1 2020
REN | Q1 2020
SG | Q2 2020
TERNA | Q2 2020
NG | June 2020
RTE | June 2020
PSE | Q1 2021

## Slide 18: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
Region CZ-PL
Timeframe to reflect TSO forecast go-live dates
// run extension if needed
// run region-E
// run region-W
REE
SG
NG
CEPS
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July
REN
TERNA
RTE
PSE
f/c GL Q1 2021
GL
(Stand-alone)

## Slide 19: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
Following aspects can be checked from platform reports:
Clearing result gap size
Outcomes & assessment

## Slide 20: 5. Parallel Run phase, BSP involvement and planning for Go-Live(s)
Confirmation of each TSO expected Go-live date (affects planning of end of parallel run)
Participation of BSPs (local organisation)
Open points

## Slide 21: Topic 6: Transparency and publication

## Slide 22: 6. Transparency and publication
Libra undertakes transparency reporting in accordance with Transparency Regulation (TR) and Guideline on Electricity Balancing (EB GL).
Following articles are in scope for Libra:
  TR art. 17.1.f – Balancing energy prices
  EB GL art. 12.3.b&c - Balancing energy bids and their conversion
  EB GL art. 12.3.e(iii & iv) – Aggregated offered, activated and unavailable balancing energy bids
Legal background
Transparency reporting from Libra

## Slide 23: 6. Transparency and publication
Reporting performed according to ENTSO-E Manual of Procedures v3r2.
Libra reports on standard RR product only.
Data reported for all scheduling areas connected to the Libra platform.
Data delivered for every hour at H+30 the latest, with 15-minute resolution.
Implementation
Transparency reporting from Libra

## Slide 24: Topic 7: Q&A

## Slide 25: Thanks!