## Slide 1: TERRE Trans European Replacement Reserves Exchange
ENTSO E BSG meeting
5th of March 2018

## Slide 2: Introduction and Project current state

## Slide 3: Introduction and Project current state
Current status
Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06
TSO-TSO Platform design
LIBRA platform development
2016
2017
2018
2019
TSO-BSP/BRP RR market design
GO Live window
Public Consultation and NRA support
TSO-TSO design:
CBA
Definition of the product
Imbalance need
Central Dispatch
Unshared and Restricted bids
Algorithm
Settlement
Timings
RR market design
TSO-TSO model
TSO-BSP/BRP model
Accepted RR Product
Harmonisation of incentives/settlement rules/deviations
BEGCT definition
Transparency regulation
Implementation Framework
Involvement of all RR countries into discussion
LIBRA TSO-TSO rules and desing
RR market rules and design
Governance and cost-sharing rules
Development of the
LIBRA platform
Functional design
Development main modules LIBRA
Testing (IOP and E2E)
Contracting of services
I.
II.
III.
IV.
//run
Implementation Framework (GL EB requirements)
Today
TERRE Website updated via link:
https://electricity.network-codes.eu/network_codes/eb/terre/

## Slide 4: Project
Geographical scope
Participants
  Membres/Observers:
  France (Rte)
  Italy (Terna)
  Portugal (REN)
  Spain (REE)
  Swiss (Swissgrid)
  GB (National Grid)
  Czech Rep
  Roumania
  Poland
  Hongry
  Bugaria
  Greece
  Norway
  Ongoing:
  Suède
  Finlande
  Danemark
RR users
Observer

## Slide 5: TERRE 2nd consultation

## Slide 6: 2. TERRE consultation feedback
2 Consultation Phase (Reminder)
High level planning past consultation on RR market design
Main topics consulted
TSO-TSO
Model
Marginal Price
Congestion rent management
Timings: XB scheduling step of 60’ with target of 15’
Allowance of Counter-Activations
UAB/URB treatment
Need flexibility
Interconnection controllability
TSO-BSP/BRP
Model
Accepted RR balancing product definition
Harmonization of settlement rules
Harmonization of incentives
BEGCT definition
Transparency
National publications
Publications on ENTSO-e transparency platform
Harmonization issue
Validation period
Approval package
Stakeholder meeting
NRAs Submission
Validation
Stakeholders
Period
Assessment
30th June- 16th August
Jul 24th - Sep 20th
Sep 29
6 weeks
Drafting and Validation period
Consultation
PHASES
3 weeks
4 weeks
At a working level, the NRAs sent their « Common Opinion » on the TSOs submission.

## Slide 7: 2. TERRE consultation feedback
Main topics to be addressed by the project (NRAs feedbacks)
Counter Activation
BEGCT
Increasing of RR daily clearings number (48 or 96)
Reduction of XB Scheduling Step for Balancing market
Local/National Stakeholder involvement
The TSOs are still assessing the NRAs opinion paper.
The current version of the RR IF doesn’t tackle all NRA proposals
Drafted with 11 TSOs (6 TSOs was involved in the 2 previous consultations)
The RR IF includes mainly what the GL EB required for the “RR Platform”

## Slide 8: Implementation Framework

## Slide 9: RR Market
Implementation Framework-Planning
NRAs approval consultation on RR market harmonization
Validation by NRAs
Consultation phase
Drafting period
Assessment and update
3 weeks
Week
4th of June
6 Weeks
1 month
ENTOS E Market committee (RR) approval
2 weeks
6 months
Consultation
IF phase
TSOs
approval
RR market consultation
Market committee approval
ENTSO E Market committee (RR) approval
Submission to NRAs
Early May
4th April
21st of Feb
1st of February
General planning – NRAs support

## Slide 10: RR Market
Implementation Framework-Content
Overview content following GLEB
Content defined in EBGL
High level design of the platform
Roadmap and timelines for implementation
Definition of the functions required to operate the platform
Rules for governance and operation of entity operating the platform and Proposed appointed entity
Cost sharing principles
Framework for harmonization of terms and conditions
BEGCT
TSO-TSO GCT
Standard product
CMOL (LIBRA PF)
Description of the algorithm for the activation optimization (LIBRA PF)
TSO answer to stakeholders’ responses to the IF Consultation

## Slide 11: Executive summary
Public Consultation link: consultation for the implementation framework for European platform for replacement reserves
Next TERRE Stakeholder Workshop on RR IF link: registration is open
As required by the GLEB, all TSOs using RR have 6 months after the EIF of GLEB to submit a proposal for the RRIF. The deadline is thus 18 June 2018.
The work is handled by the TERRE project, in which all TSOs using Replacement Reserves are represented. It must be noticed that ESO joined the project in January 2018.
In addition, an explanatory note to the RRIF has been written to help stakeholders’ understanding.
RRIF memorandum

## Slide 12: RRIF Content overview
RRIF is developed by all Transmission System Operators performing the reserve replacement process pursuant to Part IV of Regulation (EU) 2017/1485 of 2 August 2017 regarding the RRIF for a European platform for the exchange of balancing energy from replacement reserves (referred to as “RR-Platform”).
RRIF takes into account the general principles and goals set in Commission Regulation (EU) 2017/2195 of 23 November 2017 establishing a guideline on electricity balancing ( “GL EB”), Commission Regulation (EU) 2017/1485 establishing a guideline on electricity transmission system operation (“GL SO”) as well as Regulation (EC) No 714/2009 of the European Parliament and of the Council of 13 July 2009 on conditions for access to the network for cross-zonal exchanges in electricity ( “Electricity Regulation”)
RRIF lays down the design, functional requirements, governance and cost sharing for the RR-Platform. In addition, the RRIF contains the proposal for the entity to perform the functions of the proposal. The European RR-Platform shall be able to perform the functions described in Article 5 on this RRIF and as described in the Article 19(3) of the GL EB
RRIF proposal fulfil the content described by the Article 19(3) of the GL EB
RRIF proposal fulfil the content described by the Article 3 of the GL EB
Whereas

## Slide 13: LIBRA

## Slide 14: LIBRA Platform
Description and last status
Hosting
External party will be contracted for hosting the LIBRA activities
Flexibility on changing the hosting party towards other suppliers or TSOs
Flexibility on upgrading the hardware following future demand
IT monitoring service
Monitoring of the Optimization module initially 24/7, with the possibility to decrease to 8/7 after the // run
Monitoring of the IT interface: 24/7
SLAs and contracting in case of failure
Financial Settlement
Financial settlement externally contracted
Monthly billing system between TSOs through a centralized clearing house
Flexibility to add new TSOs
Optimization/Clearing algorithm
Optimization of the bids using CMOL
Optimization of the available CZ interconnections
IT interface/data management
Interface scalable up to 50 TSOs
Lot B1: Tendering closed / development started
Lot C: Tendering Ongoing
Lot D
Services
Main modules
TESTING
Lot F: Tendering closed / work started
Lot B2: Tendering closed / development started
Lot C: Tendering Ongoing

## Slide 15: Thanks for your attention

## Slide 16: RR IF Detailed inputs

## Slide 17: RRIF Content overview
The RR-Platform as determined in this RRIF is the common proposal of the RR TSOs in accordance with Article 19 of the GL EB.
European platforms for imbalance netting, manual and automatic frequency restoration reserves processes are out of the scope.
The RR-Platform implements the exchange and activation of balancing energy from replacement reserves standard products, through an optimization algorithm whilst respecting the cross-zonal capacity parameters.
Articles 30 on imbalance netting process and 50 on TSO-TSO settlement of the GL EB are out of the scope of this RRIF and will be treated in a separate proposal. However, this RRIF does includes some principles in line with those articles.
Article 1: Subject matter and scope

## Slide 18: RRIF Content overview
Designated Entity: is the entity designated to operate all the RR-Platform functions;
TERRE project: is the implementation project of RR-Platform;
Member: means the RR TSO who is member of the TERRE project or RR-Platform and has decision making powers to participate in the decision-making. The TSOs member compose the consortium designated to operate all the RR-Platform functions;
Observer: means the TSO participating to the TERRE project or RR-Platform, without decision making power.
Article 2: Definitions and interpretations

## Slide 19: RRIF Content overview
The RR-Platform implements the exchange and activation optimization of standard product for balancing energy from RR, through an optimization algorithm and respecting the availability of cross-zonal capacities.
Article 3 High-level design of the RR-Platform

## Slide 20: RRIF Content overview
Six months after the approval of this proposal, all TSOs performing the RR process shall designate the proposed entity supported by this RRIF (Article 19.4 GL EB).
All TSOs performing the RR process which have at least one interconnected neighbouring TSO, performing the RR process, shall implement and make operational the RR-Platform for the exchange of balancing energy for RR no later than one year after the approval of the proposal for the RRIF for RR-Platform. A TSO may request a derogation from this requirement (Article 62 GL EB).
Article 4: The roadmap and timeline for the implementation of the RR-Platform
Validation by NRAs
Drafting period
Assessment and update
2 weeks
June
1 month
1 month
MC(RR)
Sending
2 weeks
6 months
Consultation
RRIF Approval
Market committee approval
RR market consultation
Market committee approval
Market committee (RR) approval
Submission to NRAs
22nd May
1st April
Mid Feb- Mar
10thJan
Assessment and update
1st of Feb
MC(RR)
Approval

## Slide 21: RRIF Content overview
The RR-Platform shall consist of the following functions:
  AOF (Activation optimization function)
  Data management:
    Common merit order list;
    Available cross-zonal capacity.
  TSO-TSO settlement.
It is the responsibility of the Designated entity as described in Article 10 to operate and monitor the RR-Platform and to provide adequate hosting facilities.
Article 5: Functions of the RR-Platform

## Slide 22: RRIF Content overview
The product exchanged in RR-Platform is the standard product for balancing energy from RR (“RR standard product”).
Article 6: Definition of the RR Standard Products
Standard Characteristics | 
Mode of activation | Manual and scheduled
Preparation Period | From 0 to 30 min
Ramping Period | From 0 to 30 min
FAT | 30 min
Deactivation Period | Under national responsibility
Minimum quantity | 1 MW
Maximum quantity | In case of divisible bid, no max is requested only technical limit (IT limit). In case of indivisible bid, national rules will be implemented
Minimum duration of delivery period | 15 min
Maximum duration of delivery period | 60 min
Location | Bidding Zones
Validity Period | Defined by BSP and respecting the min and max delivery period
Minimum duration between the end of deactivation period and the following activation | Recovery Period = determined by BSP
Divisibility | Divisible and/or indivisible bids allowed (Resolution for divisible bids = 0,1MW)
Price of the bid | Defined by the BSPs €/MWh
Time Resolution | 15 min

## Slide 23: RRIF Content overview
The gate closure time (GCT) for the submission of an RR standard product balancing energy bid to the connecting TSO by BSPs shall be between 60 and 55 minutes before the period which is concerned by the activation of the RR standard product to satisfy the TSO balancing energy need.
For TSOs applying central dispatching model, the GCT for RR integrated scheduling process bids shall be defined pursuant to Articles 24(5) and 24(6) of the GL EB.
No later than two months prior to the entry into operation of the RR-Platform, all TSOs performing the RR process shall develop a proposal to define the Balancing Energy Gate Closure Time for RR standard product energy bids.
Article 7: Gate closure time for RR standard product energy bids

## Slide 24: RRIF Content overview
The gate closure time for the submission of the RR standard product energy bids to the common merit order list function by the connecting TSO shall be between 45 and 36 minutes before the before the period which is concerned by the activation of the RR balancing energy bid to satisfy the TSO balancing energy need.
The TSOs will send the RR balancing energy need and cross-zonal capacities before the TSO energy bid submission gate closure time for RR.
No later than two months prior to the entry into operation of the RR-Platform, all TSOs performing the RR process shall develop a proposal to define the TSO energy bid submission gate closure time for RR pursuant
Article 8: TSO energy bid submission gate closure time for RR

## Slide 25: RRIF Content overview
Each BSP in self-dispatch system shall submit the RR standard product energy bids to the connecting TSO.
Each BSP in central-dispatch system shall submit integrated scheduling process bids to the connecting TSO who shall convert integrated scheduling bids received from BSPs into RR standard product energy bids.
The format possibilities of the RR standard product energy bids are:
  Divisible or indivisible;
  Exclusive in volume or time and/or Multi-part in volume and price;
  Linked in volume or time.
The connecting TSO shall submit the coherent bids to the common merit order list function.
The common merit order list function shall create two merit order lists that shall contain all involved RR standard product energy bids and all the RR balancing energy needs submitted by the TSOs:
Article 9: CMOL to be organised by the activation optimisation function

## Slide 26: RRIF Content overview
  RR TSOs will designate the RR TSOs as entity for operating together by means of TERRE consortium the AOF.
  RR TSOs will designate the RR TSOs as entity for operating together by means of TERRE consortium the data management function.
  RR TSOs will designate the RR TSOs as entity for operating together by means of TERRE consortium the TSO-TSO settlement function.
The TERRE consortium is composed of all Members. The governance and decision making rules of this consortium are in accordance with the GL EB as described in Article 10(2) and (3) of this RRIF.
Article 10: Rules for governance, operation of entity and proposed designated entity
Designation of Entity

## Slide 27: RRIF Content overview
  Representation of each RR TSO through the steering committee and (expert) groups
  The steering committee is the decision-making body of the RR-Platform and will notably:
  Provide guidance and binding decisions on the RR-Platform;
  Inform ENTSO-E;
  Informs NRAs;
  Validates analysis and outputs from the expert groups
  In addition, all RR TSOs will follow the GL EB governance and operation of the RR-Platform based on:
  principle of non-discrimination
  ensuring equitable treatment of all RR TSOs
  Ensuring no TSO benefits from unjustified economic advantages through the participation in the functions of the RR-Platform
Article 10: Rules for governance, operation of entity and proposed designated entity
Governance rules followed by TERRE consortium

## Slide 28: RRIF Content overview
  An effective coordination and decision-making process to resolve any conflicting positions within the consortium establishing the Designated entity will be set up based on the following rules:
  TSOs deciding on proposals for terms and conditions or shall decide by qualified majority.
  Since the TERRE project is composed of more than five RR countries, decision shall require majority of:
  Members representing at least 72 % of the RR countries concerned; and
  Members representing RR countries comprising at least 65 % of the population of the concerned region.
  A blocking minority for decisions must include at least a minimum number of TSOs representing more than 35 % of the population of the participating RR countries, plus TSOs representing at least one additional RR country concerned, failing of which the qualified majority shall be deemed attained.
Article 10: Rules for governance, operation of entity and proposed designated entity
Decision making

## Slide 29: RRIF Content overview
The operation rules will be agreed between the RR TSOs
These operation rules will elaborate on technical details on how:
  the RR TSOs will use the RR-Platform
  the local systems will be connected to the RR-Platform. The RR TSOs will also outline operational aspects such as exception handling, fall-back measures; and
  to raise and escalate incidents.
Article 10: Rules for governance, operation of entity and proposed designated entity
Operation rules

## Slide 30: RRIF Content overview
RR balancing energy need submitted by the TSOs to the RR-Platform has several characteristics:
Article 11: Framework for harmonization of terms and conditions
RR balancing energy need
Minimum size | 1 MW
Minimum delivery period | 15 min
Max delivery period | 60 min
Location | Bidding zones (ex: several needs for Italy)
Maximum Size | The maximum size of the RR balancing energy need submitted by the TSO for its LCF area should be less or equal to the sum of the shared Offers made in the same direction. Under certain conditions, a TSO can notify the system which will apply an exemption to this rule
Divisible Volume | Under the responsibility of TSO to a resolution of 1MW
Price | For inelastic needs TSOs will not price their needs. For elastic needs a price will be submitted, which will set a min/max price each TSO is willing to receive/pay to satisfy its needs. Its resolution is 0.01€/MWh.
Time Resolution | 15 min
Firmness | Yes
Direction | Positive (system short) or Negative (system long)
Tolerance Band in volume | Parameter under the responsibility of RR TSO

## Slide 31: RRIF Content overview
The RR TSOs will be allowed to submit a desired flow to RR-Platform for a specific interconnection.
Article 11: Framework for harmonization of terms and conditions
Controllability of interconnection
Cap and floors prices
The TSOs suggest to not apply caps and floors to the balancing energy offers submitted to RR-Platform. Only technical price limit will be applied (IT limits).
Harmonized Cross-Zonal scheduling steps and number of daily clearings
The RR TSOs will reduce the cross-border scheduling steps to less than 60min for the borders included in RR region
At the launch of the RR-Platform, the number of daily gates will be 24

## Slide 32: RRIF Content overview
To become a BSP it is necessary to perform a qualification
The BSPs for RR must be able to provide a RR standard product and exchange necessary information with the TSO
The BSPs will be settled for the requested volume of energy;
The BSPs will receive the cross-zonal marginal price.
The BSP will identify the location of the product in non-portfolio bidding systems;
In case of under or over delivery of balancing energy, the BSP will have financial consequences directly or through the BRP;
The terms and conditions for BRPs are out of the scope of the RR-Platform implementation
Article 11: Framework for harmonization of terms and conditions
Terms and conditions for BSPs of RR standard product

## Slide 33: RRIF Content overview
The cost sharing between the TSOs in different RR countries will be based on the principles in accordance with Article 23 of the GL EB.
The costs associated with the establishing, amending and operation of RR-Platform are broken down into:
  Common costs resulting from RR-Platform development costs, costs required for external support to the project and the Project Management Office (PMO) costs.
  The historical costs will include all the common costs, incurred from January 2017 and excluding the PMO costs.
Observers in the TERRE project will participate only to the PMO costs.
Members will contribute to the common costs and the historical costs.
Article 12: Cost Sharing Principles

## Slide 34: RRIF Content overview
The RRIF describes the:
The inputs of the optimisation algorithm
The objective functions of the optimisation algorithm
The constraints of the optimisation algorithm
The results of the optimisation algorithm
Note: In the event that the optimisation algorithm will not provide results, a fall-back procedure will be applied
Article 13: Description of the optimization algorithm